## Project plan
Masters creation
| Content brief to be provided | 2026-07-31 | Central
| Masters to be created by RMP | 2026-08-12 | RMP
| Master documents to be reviewed and feedback to be provided to RMP | 2026-08-21 | Central
| RMP to make amendments accordingly by | 2026-08-26 | Central/RMP
| Final approval from from Central (legal included) by | 2026-08-31 | Central
Source files for all segments
| Rates, zoning source files and surcharges to be provided in batches by | 2026-09-01 | Pricing
Localisation
| Translation document to be shared with local marketers by | 2026-08-28 | RMP
| Translations to be done and sent to RMP (fully approved) by | 2026-09-11 | Local teams
| RMP to localise and proof SLR Public, SLR Hidden, and FICP single documents, Locals and Pricing to approve by | 2026-11-06 | RMP/Central/Local teams
| RMP to localise and proof Default 001 single documents, Locals and Pricing to approve by | 2026-12-04 | RMP/Central/Local teams
Digital
| RMP to provide SLR Public, SLR Hidden, and FICP single documents by | 2026-11-13 | RMP
| RMP to provide Default 001 single documents by | 2026-12-11 | RMP